## Task Schedule
ID | Category | Tasks | Task .toString | Responsible | Start Date | 2016-09-01 | Duration | Finish Date | State
1 | Technology Test | Vuforia | 1. Technology Test: Vuforia | Dixon & Tim | 2016-09-01 | 0 | 6 | 2016-10-01 | Done
2 | Technology Test | GPS | 2. Technology Test: GPS | Toni | 2016-09-01 | 0 | 6 | 2016-10-01
3 | Server | Point Location Management | 3. Server: Point Location Management | Toni | 2016-10-01 | 4 | 11 | 2016-12-01
3.1 | Server | Bingo of Points Generation | 3.1. Server: Bingo of Points Generation | Toni | 2016-10-01 | 4 | 11 | 2016-12-01
4 | Server | Point Occupation | 4. Server: Point Occupation | Dixon | 2016-10-01 | 4 | 11 | 2016-12-01 | Ongoing
5 | Mobile Application | Game Information Acquisition | 5. Mobile Application: Game Information Acquisition | Toni & Tim | 2016-10-01 | 4 | 15 | 2017-01-01
5.1 | Mobile Application | Point Information Acquisition | 5.1. Mobile Application: Point Information Acquisition | Toni | 2016-10-01 | 4 | 11 | 2016-12-01
5.2 | Mobile Application | Occupation Information | 5.2. Mobile Application: Occupation Information | Dixon | 2016-10-01 | 4 | 11 | 2016-12-01
5.3 | Mobile Application | Score Acquisition | 5.3. Mobile Application: Score Acquisition | Tim | 2016-11-01 | 9 | 6 | 2016-12-01
5.4 | Mobile Application | Game Over | 5.4. Mobile Application: Game Over | Tim | 2016-12-01 | 13 | 7 | 2017-01-01
6 | Mobile Application | Point Occupation | 6. Mobile Application: Point Occupation | Dixon | 2016-10-01 | 4 | 15 | 2017-01-01 | Ongoing
6.1 | Mobile Application | AR Mini Game | 6.1. Mobile Application: AR Mini Game | Dixon | 2016-11-01 | 9 | 11 | 2017-01-01 | Ongoing
7 | Server | Server Setup | 7. Server: Server Setup | Tim | 2016-11-01 | 9 | 2 | 2016-11-01
8 | Server | Score Counting | 8. Server: Score Counting | Tim | 2016-11-01 | 9 | 6 | 2016-12-01
9 | Server | Game Judgement | 9. Server: Game Judgement | Tim | 2016-12-01 | 13 | 7 | 2017-01-01
10 | Mobile Application | Graphics Desgin | 10. Mobile Application: Graphics Desgin | Toni | 2016-12-01 | 13 | 11 | 2017-02-01
11 | Mobile Application | New Game Creation | 11. Mobile Application: New Game Creation | Dixon | 2017-01-01 | 17 | 7 | 2017-02-01
11.1 | Mobile Application | Participation | 11.1. Mobile Application: Participation | Dixon | 2017-01-01 | 17 | 2 | 2017-01-01 | Delayed
11.2 | Mobile Application | Chat Room | 11.2. Mobile Application: Chat Room | Dixon | 2017-01-01 | 17 | 2 | 2017-01-01 | Delayed
12 | Server | New Game Creation | 12. Server: New Game Creation | Dixon | 2017-01-01 | 17 | 7 | 2017-02-01
12.1 | Server | Participation | 12.1. Server: Participation | Dixon | 2017-01-01 | 17 | 2 | 2017-01-01 | Delayed
12.2 | Server | Chat Room | 12.2. Server: Chat Room | Dixon | 2017-01-01 | 17 | 2 | 2017-01-01 | Delayed
13 | Mobile Application | User Account | 13. Mobile Application: User Account | Dixon & Tim | 2017-02-01 | 22 | 6 | 2017-03-01
13.1 | Mobile Application | User Login | 13.1. Mobile Application: User Login | Dixon & Tim | 2017-02-01 | 22 | 2 | 2017-02-01
13.2 | Mobile Application | User Register | 13.2. Mobile Application: User Register | Dixon & Tim | 2017-02-01 | 22 | 2 | 2017-02-01
14 | Server | Account and User Data Management | 14. Server: Account and User Data Management | Dixon & Tim | 2017-02-01 | 22 | 6 | 2017-03-01
|  |  | . : |  |  | -6088 | 2
|  |  | . : |  |  | -6088 | 2
|  |  | . : |  |  | -6088 | 2
|  | Search: |  | Search: |  |  |  |  | Done
Ongoing
Delayed
Blank