## Task Schedule
ID | Category | Tasks | Task .toString | Responsible | Start Date | 2016-09-01 | Duration | Finish Date | State | Completion | Remarks
1 | Technology Test | GPS | 1. Technology Test: GPS | Toni | 2016-09-01 | 0 | 6 | 2016-10-01 | Done
2 | Server | Generator Management | 2. Server: Generator Management | Toni | 2016-10-01 | 4 | 11 | 2016-12-01 | Ongoing
3 | Project | Game Information Acquisition | 3. Project: Game Information Acquisition | Toni & Tim | 2016-10-01 | 4 | 15 | 2017-01-01 | Ongoing
3.1 | Mobile Application | Generator Coordinate | 3.1. Mobile Application: Generator Coordinate | Toni | 2016-10-01 | 4 | 11 | 2016-12-01 | Ongoing
3.2 | Server | Generator Coordinate | 3.2. Server: Generator Coordinate | Toni | 2016-10-01 | 4 | 11 | 2016-12-01 | Ongoing
3.3 | Mobile Application | Domination Status | 3.3. Mobile Application: Domination Status | Tim | 2016-10-01 | 4 | 11 | 2016-12-01 | Done
3.4 | Server | Domination Status | 3.4. Server: Domination Status | Tim | 2016-10-01 | 4 | 11 | 2016-12-01 | Done
3.5 | Mobile Application | Score Acquisition | 3.5. Mobile Application: Score Acquisition | Tim | 2016-11-01 | 9 | 6 | 2016-12-01 | Done
3.6 | Server | Score Acquisition | 3.6. Server: Score Acquisition | Tim | 2016-11-01 | 9 | 6 | 2016-12-01 | Done
3.7 | Mobile Application | Game Over | 3.7. Mobile Application: Game Over | Tim | 2016-12-01 | 13 | 7 | 2017-01-01 | Ongoing
3.8 | Server | Game Over | 3.8. Server: Game Over | Tim | 2016-12-01 | 13 | 7 | 2017-01-01 | Ongoing
4 | Project | Dominate Generator | 4. Project: Dominate Generator | Dixon | 2016-10-01 | 4 | 20 | 2017-02-01 | Ongoing | 65% | Major workload is about 4.1.
4.1 | Mobile Application | "Satellite Hack" Mini Game | 4.1. Mobile Application: "Satellite Hack" Mini Game | Dixon | 2016-10-01 | 4 | 15 | 2017-01-01 | Ongoing | 60% | Delayed due to examination. Suppose to catch up in Feb-17.
4.2 | Mobile Application | Dominate Generator | 4.2. Mobile Application: Dominate Generator | Dixon | 2017-01-01 | 17 | 7 | 2017-02-01 | Done | 100% | Earlier than schedule due to ease of task.
4.3 | Server | Dominate Generator | 4.3. Server: Dominate Generator | Tim | 2016-10-01 | 4 | 11 | 2016-12-01 | Done
5 | Server | Server Setup | 5. Server: Server Setup | Tim | 2016-10-01 | 4 | 7 | 2016-11-01 | Done
6 | Server | Score Counting | 6. Server: Score Counting | Tim | 2016-11-01 | 9 | 6 | 2016-12-01 | Done
7 | Server | Game Judgement | 7. Server: Game Judgement | Tim | 2016-12-01 | 13 | 7 | 2017-01-01 | Ongoing
8 | Mobile Application | Graphics Desgin | 8. Mobile Application: Graphics Desgin | Toni | 2016-12-01 | 13 | 15 | 2017-03-01 | Ongoing
9 | Project | New Game Creation | 9. Project: New Game Creation | Dixon | 2017-02-01 | 22 | 6 | 2017-03-01 |  | 0%
9.1 | Mobile Application | Participation | 9.1. Mobile Application: Participation | Dixon | 2017-02-01 | 22 | 6 | 2017-03-01 |  | 0%
9.2 | Server | Participation | 9.2. Server: Participation | Dixon | 2017-02-01 | 22 | 6 | 2017-03-01 |  | 0%
9.3 | Mobile Application | Chat Room | 9.3. Mobile Application: Chat Room | Dixon | 2017-02-01 | 22 | 6 | 2017-03-01 |  | 0%
9.4 | Server | Chat Room | 9.4. Server: Chat Room | Dixon | 2017-02-01 | 22 | 6 | 2017-03-01 |  | 0%
10 | Project | User Account | 10. Project: User Account | Dixon & Tim | 2017-03-01 | 26 | 7 | 2017-04-01 |  | 0%
10.1 | Mobile Application | User Login | 10.1. Mobile Application: User Login | Dixon & Tim | 2017-03-01 | 26 | 7 | 2017-04-01 |  | 0%
10.2 | Mobile Application | User Register | 10.2. Mobile Application: User Register | Dixon & Tim | 2017-03-01 | 26 | 7 | 2017-04-01 |  | 0%
10.3 | Server | Account and User Data Management | 10.3. Server: Account and User Data Management | Dixon & Tim | 2017-03-01 | 26 | 7 | 2017-04-01 |  | 0%
11 | Mobile Application | User interface | 11. Mobile Application: User interface | Toni | 2017-01-24 | 21 | 5 | 2017-02-12
|  |  | . : |  |  | -6088 | 2
|  |  | . : |  |  | -6088 | 2
|  | Search: |  | Search: |  |  |  |  | Done
Ongoing
Delayed
Blank