## Task Schedule
ID | Category | Tasks | Task .toString | Responsible | Start Date | 2016-09-01 | Duration | Finish Date | State
1 | Technology Test | GPS | 1. Technology Test: GPS | Toni | 2016-09-01 | 0 | 6 | 2016-10-01 | Done
2 | Server | Generator Management | 2. Server: Generator Management | Toni | 2016-10-01 | 4 | 11 | 2016-12-01 | Done
3 | Project | Game Information Acquisition | 3. Project: Game Information Acquisition | Toni & Tim | 2016-10-01 | 4 | 15 | 2017-01-01 | Done
3.1 | Mobile Application | Generator Coordinate | 3.1. Mobile Application: Generator Coordinate | Toni | 2016-10-01 | 4 | 11 | 2016-12-01 | Done
3.2 | Server | Generator Coordinate | 3.2. Server: Generator Coordinate | Toni | 2016-10-01 | 4 | 11 | 2016-12-01 | Done
3.3 | Mobile Application | Domination Status | 3.3. Mobile Application: Domination Status | Tim | 2016-10-01 | 4 | 11 | 2016-12-01 | Done
3.4 | Server | Domination Status | 3.4. Server: Domination Status | Tim | 2016-10-01 | 4 | 11 | 2016-12-01 | Done
3.5 | Mobile Application | Score Acquisition | 3.5. Mobile Application: Score Acquisition | Tim | 2016-11-01 | 9 | 6 | 2016-12-01 | Done
3.6 | Server | Score Acquisition | 3.6. Server: Score Acquisition | Tim | 2016-11-01 | 9 | 6 | 2016-12-01 | Done
3.7 | Mobile Application | Game Over | 3.7. Mobile Application: Game Over | Tim | 2016-12-01 | 13 | 7 | 2017-01-01 | Done
3.8 | Server | Game Over | 3.8. Server: Game Over | Tim | 2016-12-01 | 13 | 7 | 2017-01-01 | Done
3.9 | Mobile Application | Gameover Notification | 3.9. Mobile Application: Gameover Notification | Dixon | 2017-05-01 | 35 | 2 | 2017-05-01 | Done
4 | Project | Dominate Generator | 4. Project: Dominate Generator | Dixon & Tim | 2016-10-01 | 4 | 32 | 2017-05-01 | Done
4.1 | Mobile Application | "Satellite Hack" Mini Game | 4.1. Mobile Application: "Satellite Hack" Mini Game | Dixon | 2016-10-01 | 4 | 20 | 2017-02-01 | Done
4.2 | Mobile Application | Dominate Generator | 4.2. Mobile Application: Dominate Generator | Dixon | 2017-04-01 | 30 | 2 | 2017-04-01 | Done
4.3 | Server | Dominate Generator | 4.3. Server: Dominate Generator | Tim | 2016-10-01 | 4 | 11 | 2016-12-01 | Done
5 | Server | Server Setup | 5. Server: Server Setup | Tim | 2016-10-01 | 4 | 7 | 2016-11-01 | Done
6 | Server | Score Counting | 6. Server: Score Counting | Tim | 2016-11-01 | 9 | 6 | 2016-12-01 | Done
7 | Server | Game Judgement | 7. Server: Game Judgement | Tim | 2016-12-01 | 13 | 7 | 2017-01-01 | Done
8 | Mobile Application | Graphics Desgin | 8. Mobile Application: Graphics Desgin | Toni | 2016-12-01 | 13 | 15 | 2017-03-01 | Done
9 | Project | New Game Creation | 9. Project: New Game Creation | Tim | 2017-02-01 | 22 | 6 | 2017-03-01 | Done
9.1 | Mobile Application | Participation | 9.1. Mobile Application: Participation | Tim | 2017-02-01 | 22 | 6 | 2017-03-01 | Done
9.2 | Server | Participation | 9.2. Server: Participation | Tim | 2017-02-01 | 22 | 6 | 2017-03-01 | Done
10 | Project | Chat Room | 10. Project: Chat Room | Dixon | 2017-02-01 | 22 | 6 | 2017-03-01 | Done
11 | Project | User Account | 11. Project: User Account | Tim | 2017-03-01 | 26 | 7 | 2017-04-01 | Done
11.1 | Mobile Application | User Login | 11.1. Mobile Application: User Login | Tim | 2017-03-01 | 26 | 7 | 2017-04-01 | Done
11.2 | Mobile Application | User Register | 11.2. Mobile Application: User Register | Tim | 2017-03-01 | 26 | 7 | 2017-04-01 | Done
11.3 | Server | Account and User Data Management | 11.3. Server: Account and User Data Management | Tim | 2017-03-01 | 26 | 7 | 2017-04-01 | Done
12 | Mobile Application | User interface | 12. Mobile Application: User interface | Dixon & Toni & Tim | 2017-01-01 | 17 | 15 | 2017-04-01 | Done
13 | Document | Task List & Gantt Chart | 13. Document: Task List & Gantt Chart | Dixon | 2016-10-01 | 4 | 24 | 2017-03-01 | Ongoing
14 | Mobile Application | Project Integration | 14. Mobile Application: Project Integration | Dixon | 2017-04-01 |  | 6 | 2017-05-01 | Done
2
2
|  |  | . : |  |  | -6088 | 2
|  | Search: |  | Search: |  |  |  |  | Done
Ongoing
Delayed
Blank